## Tabelle1
Sprint Backlog 1

Backlog Posten	Priority	Verantwortlich	Status	Schätzung	Tag 1	Tag 2	Tag 3	Tag 4	Tag 5	Sprint Review
setup of Trello, Github, VisualStudio	1	everybody	WIP	4
understanding and deciding for algorithm	1	everybody	WIP	6
camera setup	1	Abbas, Rahul	done	2	2
idea for design of the GUI	4	Lukas, Florian, Habib	WIP	10
Project vision / Important substeps and mile stones / Selected process framework / Roles in the team (eg Scrum Master, Product Owner) / T i ti (j i t k k l t l ) / Team-oriented Project – CTS7 – WS 19/20 Page 6 / Team organization (j / oin / t wor / k, wor / k / place, / tools ... / )	6	Rahul, Habib	WIP	2
research on databases	6	Chisom	WIP	10

Insgesamt				34	0	0	0	0	0	0